## Version Control
FRICE LIST & ESTIMATION SHEET
Araneta SAP P2 ECC6 Implementation
Author | Michelle Dabuet
Title | P323 Araneta Phase 2 FRICE List Summary and Estimation Sheet
Status | D - Draft
Version Major | 4
Version Minor | 0
Version and Change Control
Version | Date | Author | Description
F1.0 | 9/29/2014 | Lily Gilbero | Template Version
D3.0 | 10/11/2014 | Mich Dabuet | Initial Version
D4.0 | 10/13/2014 | Lily Gilbero | Completed Version for Discussion
d5.0 | 10/15/14 | Lily Gilbero | Updated with Object Assignment and Costs

## Summary
Count of Type | Column Labels
Row Labels | FI | MM | PP | PS | SD | (blank) | Grand Total
Conversion |  | 4 | 2 | 1 |  |  | 7
Enhancement | 1 | 1 |  |  | 4 |  | 6
Interface |  |  |  |  | 1 |  | 1
(blank)
Grand Total | 1 | 5 | 2 | 1 | 5 |  | 14
Details | Mandays |  | Total | Cost |  | Total |  | Discount | FPI Cost
| ABAP | Functional |  | ABAP | Functional
FPI In Scope | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Araneta Dev't - ABAP | #REF! |  | #REF! | #REF! |  | #REF!
FPI FS Creation & Testing |  | #REF! | #REF! |  | #REF! | #REF! |  |  | #REF!
FPI Development - P2CR009 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
TOTAL | [5 empty] | #REF! |  | 0 | #REF!

## FINAL FRICE LIST_FS assignment
Legend
Araneta Group - Phase 2 Project | [5 empty] | ID | Module Description |  | Priority | Module Description |  |  | Complexity | Devt Estimate
FRICE LIST SUMMARY | [5 empty] | FI | Financials |  | 1 | Must be developed before UAT |  |  | Simple | 3
Last Update: | [5 empty] | SD | Sales & Distribution |  | 2 | Must be developed before Data Migration |  |  | Medium | 7
[6 empty] | PS | Project Systems |  | 3 | Must be developed before Go Live |  |  | Complex | 13
[6 empty] | CO | Controlling |  | 4 | Must be developed before first month end |  |  | Very Complex | 20
[6 empty] | MM | Materials Management |  | 5 | Can be developed after first month end
[6 empty] | PP | Production Planning
L
No. | FRICE ID NO. | FRICE Name | Description | JUSTIFICATION | Process Name | Module | Type |  | Priority | Frequency of Use | New ¦ Existing | Assigned to (FPI or Araneta) | Complexity | Remarks | FS Creation mandays | FS Presentation & Sign-off | ABAP Mandays | Devt Support (Funct) | Unit Testing (ABAP) | Unit Testing Support (Func) | Functional Testing Mandays | UAT Support (Funct) | UAT Support (ABAP) | Total - ABAP | Total - Funct
1 | P2-060 | Master Data upload from excel(SAP) update SUS (PH, DQ, & TB) | Read excel files of master data from SAP and save to SUS database using Uploading Items Master File Utility | Item - 80, Location - 80, category - 80, unit - 80, department - 80, division - 80, country - 80, region - 80, district - 80, zone - 80, store - 80, Discount - , Bank - 50, Reason - 50 | OTC | FI | MD | M | 1 |  | New | INID | Complex | No. 11 and 12 conso; show standard report | 3 | 1 | 13 | 3 | 1 | 1 | 5 | 5 | 5 | 19 | 18
2 | P2-061 | Mapping table via SUS for FENIX | Read textfile from FENIX and map the items of SUS using Fenix Mapping Module | 75% | RTM | FI | MD | R | 1 |  | New | JO | Complex | No. 11 and 12 conso; show standard report | 3 | 1 | 13 | 3 | 1 | 1 | 5 | 3 | 3 | 17 | 16
3 | P2-062 | Mapping table via SUS for CHASE POS | Encode SAP Code for existing items in SUS | 50% | RTM | FI | MD | R | 1 |  | New | JO | Complex | max 10 tables | 3 | 1 | 13 | 3 | 1 | 1 | 3 | 3 | 3 | 17 | 14
4 | P2-063 | Creation of ARJ File Chase POS | Create ARJ file of Items using Downloading Utility to distribute per store | 80% | RTM | FI | MD | R | 1 |  | New |  | Complex | max 10 tables | 3 | 1 | 13 | 3 | 1 | 1 | 3 | 3 | 3 | 17 | 14
5 | P2-064 | Food POS upgrade for Master File monitoring | Create Notification File and send to FTP then process in SUS | 0% | RTM | FI | MD | R | 2 |  | New | JO | Complex | max 10 tables | 3 | 1 | 13 | 3 | 1 | 1 | 3 | 3 | 3 | 17 | 14
6 | P2-065 | Food POS upgrade for Master File report update compliance | Process the Notification File in SUS and log the reports of stores who updates their Master File | 50% | RTM | FI | MD | R | 2 |  | New | INID | Complex | max 10 tables | 3 | 1 | 13 | 3 | 1 | 1 | 3 | 3 | 3 | 17 | 14
7 | P2-066 | Transaction Processor Chase | Read and Extract ARJ File downloaded from stores and save to SUS Database, Log the successful and unsuccessful files, Total no. of records processed and unprocessed, Files with Error (Background Process) | 80% | RTM | FI | MD | R | 1 |  | New | INID | Complex | max 10 tables | 3 | 1 | 13 | 3 | 1 | 1 | 3 | 3 | 3 | 17 | 14
8 | P2-067 | Transaction Processor FNX | Read and Extract ARJ File downloaded from stores and save to SUS Database, Log the successful and unsuccessful files, Total no. of records processed and unprocessed, Files with Error (Background Process) | 75% | RTM | FI | MD | R | 1 |  | New | JO | Complex | max 10 tables | 3 | 1 | 13 | 3 | 1 | 1 | 3 | 3 | 3 | 17 | 14
9 | P2-068 | SUS SO table population for upload to SAP (CHASE and FNX) | Extract sales transaction of SUS and save to staging database for SAP uploading | 50% | RTM | FI | MD | R | 1 |  | New | INID | Complex | max 10 tables | 3 | 1 | 13 | 3 | 1 | 1 | 3 | 3 | 3 | 17 | 14
10 | P2-069 | Report Generation of Succesfully generated ARJ/SO | Process the generated reports from uploaded arj files | 75% | RTM | FI | MD | R | 2 |  | New |  | Complex | max 10 tables | 3 | 1 | 13 | 3 | 1 | 1 | 3 | 3 | 3 | 17 | 14
11 | P2-070 | Sales consolidator for Forecasting to Web | using of webservice it will send daily transactions into web database | 30% | RTM | FI | MD | R | 1 |  | New | JC | Complex | max 10 tables | 3 | 1 | 13 | 3 | 1 | 1 | 3 | 3 | 3 | 17 | 14
12 | P2-071 | Web GUI for forecasting | In Build to Amount Template it'll display date-range, total FG Sold, total Gross. In Forecasting Template(Store in Metro Manila) it'll display Forecasted Gross Entry(Weekly or Daily Basis) and In Forecasting Template(Satelite Store) it'll display Forecasted Gross Entry(Monthly Basis) | 30% | RTM | FI | MD | R | 1 |  | New | JC | Complex | max 10 tables | 3 | 1 | 13 | 3 | 1 | 1 | 3 | 3 | 3 | 17 | 14
13 | P2-072 | Creation of forecasting download File | After the Forecast the user was need to click the button to save the said transaction and export it into excel file | 30% | RTM | FI | MD | R | 1 |  | New | JC | Complex | max 10 tables | 3 | 1 | 13 | 3 | 1 | 1 | 3 | 3 | 3 | 17 | 14
14 | P2-073 | User Maintenance Web via SUS | The system has utility for importing the data of User from SUS | 50% | RTM | FI | MD | R | 1 |  | New | JC | Complex | max 10 tables | 3 | 1 | 13 | 3 | 1 | 1 | 3 | 3 | 3 | 17 | 14
15 | P2-074 | Store Maintenance Web link SUS | The system has utility for importing the data of Store from SUS | 30% | RTM | FI | MD | R | 1 |  | New | JC | Complex | max 10 tables | 3 | 1 | 13 | 3 | 1 | 1 | 3 | 3 | 3 | 17 | 14
16 | P2-075 | Network Monitoring System |  |  | RTM | FI | MD | R | 1 |  | New | JO | Complex | max 10 tables | 3 | 1 | 13 | 3 | 1 | 1 | 3 | 3 | 3 | 17 | 14
17 | P2-076 | Cloud FTP |  |  | RTM | FI | MD | R | 1 |  | New |  | Complex | max 10 tables | 3 | 1 | 13 | 3 | 1 | 1 | 3 | 3 | 3 | 17 | 14
18 | P2-077 | GC/Coupon/Sodexho/Palm Card Monitoring System (Web Based) | Approval code generation, Serial No. maintenance, validity period | 30% | RTM | FI | MD | R | 1 |  | New | JC | Complex | max 10 tables | 3 | 1 | 13 | 3 | 1 | 1 | 3 | 3 | 3 | 17 | 14
19 | P2-078 | GC Redemption |  | 30% | RTM | FI | MD | R | 1 |  | New | JC | Complex | max 10 tables | 3 | 1 | 13 | 3 | 1 | 1 | 3 | 3 | 3 | 17 | 14
|  | File Naming Convention | storecodeyyyymmdd.arj
Automatic Fetch of Masterfile in Foodpos Server

## Sheet1
30 | Ongoing
75 | For Testing
80 | Tested Chase Part
50 | Programmed
90 | ready for integration testing